## Sheet1
Expected Start Date | Expected End Date | Activity | Actual Start Date | Actual End Date | Status | Remark
22/9/2022 | 23/9/2022 | SRS | 22/09/2022 | 23/09/2022 | Completed
26/9/2022 | 27/09/2022 | Design | 24/09/2022 | 27/09/2022 | Completed
28/09/2022 | 30/09/2022 | Coding | 27/09/2022 | 2022-04-10 | Completed
2022-03-10 | 2022-04-10 | UT | 2022-04-10 | 2022-06-10 | Completed
2022-06-10 | 2022-07-10 | IT | 2022-05-10 | 2022-07-10 | Completed
2022-10-10 | 2022-10-10 | Getting project ready | 2022-08-10 | 2022-10-10 | Completed
Date | Day | Activity
22/9/2022 | Thur | SRS
23/9/2022 | Fri | SRS, update 1st column (requirements) of RTM, start thinking design
26/9/2022 | Mon | Design - HLD, LLD, update 2nd column (section numbers) of RTM
27/09/2022 | Tue | Design - Seqence, class, use-case diagrams
28/09/2022 | Wed | Coding
29/09/2022 | Thur | Coding, UT testcases development
30/09/2022 | Fri | Coding, IT testcases development
2022-03-10 | Mon | Code review, UT_IT test plan, update 3rd column (function names)
2022-04-10 | Tue | UT testing, first iteration of defect correction, update 4th column (UT testcases)
2022-06-10 | Thur | Second iteration of testing and defect correction, update 5th column (IT testcases)
2022-07-10 | Fri | IT testing and first iteration of defect correction
2022-10-10 | Mon | Update all previously created documents, Github upload, presentation
2022-11-10 | Tue | Final Evaluation (mock demo in case BU SME not coming this day)
2022-12-10 | Wed | Final evaluation